## Hoja 1 - COSC 412 Gantt Chart
COSC 412 Gantt Chart
PROJECT NAME: |  | StayFit
PROJECT MANAGER: |  | Oleg Lebediev
STARTING PROJECT DATE: |  | 2017-08-31
Days
ORDER | Tasks |  | Starting Date |  | Finish Date | Nivel 1 | Nivel 2 | Nivel 3 | Nivel 4 | Days
1 | Requirements Gathering |  | 2017-08-31 | 0 | 2017-09-07 | 7 |  |  |  | 7
1.1 | Planning |  | 2017-08-31 | 0 | 2017-09-07 |  | 7 |  |  | 7
1.1.1 | Assign roles |  | 2017-08-31 | 0 | 2017-08-31 |  |  | 0
3.1.1 | Use case/ sequence diagrams |  | 2017-09-02 | 2 | 2017-09-09 |  |  | 7 |  | 7
2 | Design and Analysis |  | 2017-09-08 | 8 | 2017-09-22 | 14 |  |  |  | 14
2.1 | High Level Architecture Diagram |  | 2017-09-08 | 8 | 2017-11-09 |  | 62
2.1.1 | Class Diagram |  | 2017-08-09 | -22 | 2017-09-13 |  |  | 35
3.1.1 | Interface Specifications |  | 2017-09-08 | 8 | 2017-09-16 |  |  | 8 |  | 7
3 | Site Development |  | 2017-09-23 | 23 | 2017-11-30 | 68 |  |  |  | 56
3.1 | HTML Design and Creation |  | 2017-09-23 | 23 | 2017-11-30 |  | 68 |  |  | 56
3.1.1 | Backend Software |  | 2017-09-29 | 29 | 2017-11-26 |  |  | 58 |  | 49
3.1.1.1 | Database Integration |  | 2017-09-29 | 29 | 2017-11-26 |  |  |  |  | 49
3.1.1.1.1 | Achievement Tracking |  | 2017-10-15 | 45 | 2017-11-26 |  |  |  |  | 42
3.1.1.1.1.1 | Transaction Process and Vendor Serv Integrat |  | 2017-09-29 | 29 | 2017-11-30 |  |  |  |  | 49
| Testing and Maintenance |  | 2017-12-01 | 92 | 2017-12-15 |  |  |  |  | 14
4 | Alpha Testing |  | 2015-12-01 | -639 | 2017-12-15 |  |  |  |  | 14
4.1 | Beta Testing |  | 2015-12-01 | -639 | 2015-12-15 |  |  |  |  | 14
|  |  |  | -41516 |  | 0
|  |  |  | -41516 |  |  | 0
|  |  |  | -41516 |  |  |  | 0
|  |  |  | -41516 |  |  |  |  | 0
1) If you want to add a row, first you must add it manually below the last task row. Then copy and paste the rows located in “Copy-Paste Rows” and paste it in the added row.
2) Adjust the chart according the space in the section “WEEKS”. You should stick the right edge of the last column (Person) with the left edge of the chart, and modify the lenght to match it with the quantity of weeks of each task.
3) Only box with blue dates/numbers must be changed according your needs.
4) Chart colors are according to levels. Level 1 is the red chart. Level 2 is the orange chart and level 3 is the violet chart.
Formulas:
Finish Date = [Starting Date]+[Days]